## 250.840 TO 251.025
NHLML -National Highways Logistics Management Limited
TRENCHING & DUCTING VALIDATION SHEET For Open Trench
Project Name | NHLML_DARK FIBER PROJECT (HYDERABAD to BANGALORE)
Contractor | STERLITE TECHNOLOGIES LTD
Date | 2024-03-08
Measurement Book Number (MBN) | MBN/Trenching & Ducting/MS 290 TO 291
Sheet Number
Section Name | TR5 TO TR6
State Name | ANDHRA PRADESH
PIU | ANANTHAPUR
Package | Package 3
S. No. | Chainage |  | Actual Length (Mtr) | RoW ref. LHS/RHS | Approved RoW as per RFP (Mtr) | Width available in utility corridor from RoW Boundary wall | Actual RoW available (Mtr) | Trench Details | [6 empty] | Bedding Details |  | Bend details (Yes/No) | Duct Joint Details |  | No. of Ducts Laid as applicable |  | Duct Protection |  | End caps provided (Y/N) | Coupling Point location | Remarks
| From | To | [5 empty] | Methodology Open Trench (OT) | Crossing by Hume Pipe on Interchange (Y/N) | X (Offset) in (Mtr) | D (Depth) in (Mtr) | Top Width in MM | Bottom Width in MM | Strata | Height mm | Ramming |  | Check Cleanliness of duct at either end | Visual check for tightness of coupler | 63/50 mm (Violet, Grey, Red) | 40/33 mm Blue, Yellow, Brown) | PCC/RCC/GI/DWC/ Tiles | Length (Mtr)
1 | 290.15 | 290.2 | 50 | LHS | 30 | 1.2 | 30 | OT | NA | 29.5 | 1.5 | 750 | 500 | MIXED | NA | NA | N | NA | NA | 3 | 3 | DWC | 6 | NA | NA | Ch-290.260-290.266 , depth=0.9m
2 | 290.2 | 290.25 | 50 | LHS | 30 | 1.2 | 30 | OT | NA | 29.5 | 1.5 | 750 | 500 | MIXED | NA | NA | N | NA | NA | 3 | 3 | NA | 0 | NA | NA
3 | 290.25 | 290.3 | 50 | LHS | 30 | 1.2 | 30 | OT | NA | 29.7 | 1.3 | 750 | 500 | MIXED | NA | NA | N | NA | NA | 3 | 3 | NA | 0 | NA | NA
4 | 290.3 | 290.35 | 50 | LHS | 30 | 1.2 | 30 | OT | NA | 29.5 | 1.5 | 750 | 500 | MIXED | NA | NA | N | NA | NA | 3 | 3 | NA | 0 | NA | NA
5 | 290.35 | 290.4 | 50 | LHS | 30 | 1.2 | 30 | OT | NA | 29 | 1.5 | 750 | 500 | MIXED | NA | NA | N | NA | NA | 3 | 3 | NA | 0 | NA | NA
6 | 290.4 | 290.45 | 50 | LHS | 30 | 1.2 | 30 | OT | NA | 29 | 1.4 | 750 | 500 | MIXED | NA | NA | N | NA | NA | 3 | 3 | NA | 0 | NA | NA
7 | 290.45 | 290.5 | 50 | LHS | 30 | 1.2 | 30 | OT | NA | 29 | 1.5 | 750 | 500 | MIXED | NA | NA | N | NA | NA | 3 | 3 | NA | 0 | NA | NA
8 | 290.5 | 290.55 | 50 | LHS | 30 | 1.2 | 30 | OT | NA | 28.5 | 1.5 | 750 | 500 | MIXED | NA | NA | N | NA | NA | 3 | 3 | NA | 0 | NA | NA
9 | 290.55 | 290.6 | 50 | LHS | 30 | 1.2 | 30 | OT | NA | 28.5 | 1.5 | 750 | 500 | MIXED | NA | NA | N | NA | NA | 3 | 3 | NA | 0 | NA | NA
10 | 290.6 | 290.65 | 50 | LHS | 30 | 1.2 | 30 | OT | NA | 28.5 | 1.5 | 750 | 500 | MIXED | NA | NA | N | NA | NA | 3 | 3 | NA | 0 | NA | NA
11 | 290.65 | 290.7 | 50 | LHS | 30 | 1.2 | 30 | OT | NA | 28.5 | 1.7 | 750 | 500 | MIXED | NA | NA | N | NA | NA | 3 | 3 | NA | 0 | NA | NA
12 | 290.7 | - | 0 | LHS | 30 | 1.2 | 30 | OT | NA | 28.5 | 1.6 | 750 | 500 | MIXED | NA | NA | N | NA | NA | 3 | 3 | NA | 0 | NA | NA
550
Particulars | Contractor Representative | [8 empty] | Authority Engineer Representative | [7 empty] | NHLML Representative
Signature
Name
Designation
Date