To Dynamic Planners PLC

Addis Ababa

Ref: Project Name

**Sub: Proposal for the change in arrangement in Valves and fitting**

In reference to our contract for the supply and installation of HDPE Pipe replacement Project, Contract No AAWSA/WSIDD/GOV/W003/2022, we have thoroughly examined the proposed valves and fitting on the design and we are hereby proposing an amendment as per attached list

The bases of our proposal is as follows:

1. **HDPE Valves:** Gate valves for Normal HDPE are not available in the market anymore and shall be substituted by a flanged gate valve of respective diameters.
2. **Intermittent Valves:** We are proposing intermittent valves along the main line under replacement that will help AAWSA operation department to close and open segments under maintenance ; and partial distribution of water under shifts.
3. **End caps:** Two sub lots Degole to Don Dental and Oromia to Gibson Schools under replacements have no continuity at the end and we have proposed end caps.
4. **Bends:** Due to the change in routing of the pipes we faced on the ground, some piping layouts have to be re- routed against the design given previously. Therefore the bends and elbow arrangement has to be amended accordingly and we have amended the size , and quantity
5. **Change in commercial size:** Some commercial sizes mentioned on BOQ, like 300mm, are not available and we propose to be changed 315mm Nominal Diameter
6. **Ancillary Valves:** In some segments, we are proposing Air Valves and wash out valves
7. **Bulk Meter:** There is an existing Bulk meter on Gibson site , and It hasn’t been included as to be relocated or New meter be provided

Therefore we would request your office to consider this proposal and kindly request to amend the Bill of quantity and accordingly we will be submitting our cost for your approval

Sincerely

Getu Ambaw