## Slide 1: CAT Program Management Review
Thermal Powerplant Section
Presented by:
John Pickering

## Slide 2
Weaponization
  Full Environmental Qualification
  15-Year Shelf Life
  Built-In Test with Weapon Focus
Increased Agility
  Improved Prolonged, High-Rate Maneuver Tolerance
    Working Fluid Management
  Improved Speed-Change Flexibility
    Faster PPS Execution of Speed-Change Commands
    Reduced “Lock-Out” Time Between Speed-Change Commands
DFM/DFA
  Reduced Parts Count
  Improved Modular Assembly
  Material Availability / Obsolescence (Turbine Wheel Material, Boiler Tubing)
EDM-2 Powerplant Section (PPS) Primary Development Efforts

## Slide 3: EDM-2 Powerplant Architecture
Cast Exhaust Housing
DFM/DFA Wiring Harness
Weight: < 90 lb goal
Length: 37.26 inches
Integrated Tank and Condenser Hull
Cast Nozzle Assembly
All-Attitude, Hybrid-Lubrication Geartrain
All-Attitude Centrifugal Hotwell
Improved Start-to-FW Interface
3500 psig Helium Flask Integral w/ Start Accumulator
Cast Pump Housing w/ Controls
High-Strength
Condenser w/ Reduced Working-Fluid Inventory
Improved-Agility Boiler
Powerplants Delivered for Integration based Solely on Test-Set Verification

## Slide 4
Powerplant Section Assembly

## Slide 5: EDM-2 PPS Functional Block Diagram
Seven (7) Powerplant Subsystems

## Slide 6: EDM-2 Boiler Assembly
Small-Bore Tubing
Medium-Bore Tubing
Ex-Large-Bore Tubing (Inconel 625)
Variable-Bore Coil
Increased Speed-Change Agility
Reduced Water Inventory & Inventory Shift
Inconel 625 Tube at Steam Discharge End
High Carbon SS-316 Availability Issues
Increased Safety Factor on Tube Rupture
Large-Bore Tubing

## Slide 7
Major Accomplishments since Last PMR
Completed Developmental EDM-2 Boiler Parts & Weldment Drawings
Procured Parts for in-house Fab of 10 Dev. EDM-2 Boilers – Fueling & Final Assembly in Progress
Ordered 20 Dev. EDM-2 Boiler Vessel Weldments from Vendor
Successfully Integrated Dev. EDM-2 Boiler with T/G in Powerplant System Test PP2-1-1
Near-Term Efforts
  Complete Deliverable EDM-2 Boiler Parts & Weldment Drawings
  Conduct Boiler Bullet-Impact Test
  Conduct Boiler Standalone Tests & Support PPS System Tests
EDM-2 Boiler
Task Description | Scheduled Completion Date | Status
Design EDM-2 Boiler (Developmental) | 8/2/11 | Complete
Build EDM-2 Boilers (Developmental) | 12/2/11 | 

## Slide 8: EDM-2 Turbine/Geartrain Assembly
Integrated w/ FW Liquid/Vapor Separator
Cast Nozzle
Passive Gearbox Lubrication
Integrated Star Gears
Cast Exhaust Housing
Dev. EDM-2 Turbine/Geartrain Installed in Test Shell

## Slide 9
Major Accomplishments since Last PMR
Completed EDM-2 Drawings of all Major T/G Components and Inseparable Assemblies
Completed Full-Power Testing of Developmental EDM-2 T/G on Facility Steam (TG2-5-1 & TG2-5-2)
Successfully Integrated Dev. T/G with Boiler in Powerplant System Test PP2-1-1
Ordered First Lot of Deliverable EDM-2 T/G Components
Near-Term Efforts
  Continue to Order, Receive, Inspect, & Assemble EDM-2 Hardware
  Support Powerplant System Test PP2-2-1
EDM-2 Turbine/Geartrain
Task Description | Scheduled Completion Date | Status
Design EDM-2 Turbine/Geartrain | 8/2/11 | Complete
Build EDM-2 Turbine/Geartrains | 3/6/12 | 
Test EDM-2 Turbine/Geartrains | 4/24/12 | 

## Slide 10: EDM-2 Condenser / Oxidant Assembly
Oxidant Tank Integral w/ Condenser Hull
DFM Oxidant Flow-Control Module
High-Taper Condenser Passages for Reduced Water Inventory
Simplified Condenser Inlets
One-Piece Aluminum Oxidant Bulkhead
Increased Cable Pass-Thru Area
Pyrotechnic Cold-Start Heater
High Bending-Strength Aluminum Hull (7055-T76511)

## Slide 11
EDM-2 Condenser Fabrication

## Slide 12
EDM-2 Condenser Fabrication
Condenser Inner Shell During Inspection (CMM) @ Vendor

## Slide 13
Oxidant Tank Bulkheads
EDM-1
DFM
Titanium (Ti-6Al-4V)
Six Pieces – Welded Construction
Aluminum (7075-T73)
One Piece – No Welds
Redundant O-ring Seals

## Slide 14: EDM-2 Condenser & Oxidant System
Major Accomplishments since Last PMR
Completed EDM-2 Condenser Drawings
Ordered 5 Prototype EDM-2 Condensers (2 Delivered 9/23/2011)
Completed ~ 75% of EDM-2 Oxidant System Parts Drawings
Began Procurement of Prototype EDM-2 Oxidant Components
Near-Term Efforts
Order Deliverable EDM-2 Condensers
Conduct Oxidant Flow Control System Proof Testing
Task Description | Scheduled Completion Date | Status
Design EDM-2 Condenser | 4/1/11 | Complete
Build EDM-2 Condensers | 10/31/11 | 
Test EDM-2 Condenser | 11/29/11 | 
Design EDM-2 Oxidant System | 8/2/11 | 
Build EDM-2 Oxidant System | 9/7/11 | 
Test EDM-2 Oxidant System | 10/3/11 | 

## Slide 15: EDM-2 Feedwater System Assembly
FW Pump w/ Cast Housing
Centrifugal Hotwell w/ Cast Housing
Liquid/Vapor Separator Integrated w/ Aft Gearbox Housing
Large Cable Pass-Thru
Prototype EDM-2 FW Pump Housing (Machined)
Prototype
EDM-2 Hotwell

## Slide 16
EDM-2 Feedwater System
Hotwell
Bearings
Pumping Elements
(Gear Pump)
FW Pump Housing
L/V Separator Pumping Element
(Gerotor)
Aft Gearbox Housing

## Slide 17: EDM-2 Feedwater System
  Major Accomplishments since Last PMR
Completed All EDM-2 FW System Component Drawings
Completed Centrifugal Hotwell Testing (FW2-2-1 & FW2-2-4)
Completed Liquid/Vapor Separator Testing (FW2-2-2)
Completed Hotwell Vent Testing (FW2-2-3)
Completed Pump Shaft Torque Tests (FW2-3-1)
Procured Prototype Units of all EDM-2 FW System Parts
  Near-Term Efforts
Complete FW Pump Characterization Test (FW2-3-3)
Integrate FW System into Powerplant System Test PP2-2-1
Task Description | Scheduled Completion Date | Status
Design EDM-2 Feedwater System | 8/2/11 | Complete
Build EDM-2 Feedwater Systems | 12/13/11 | 
Test EDM-2 Feedwater System | 1/18/12 | 

## Slide 18: EDM-2 Start System Assembly
3500 psi Hermetic Helium Flask Integral w/ Accumulator Sleeve
Annular Water Storage w/ Expansion Volume for Freezing
Integrated Flow Passages
Simplified Interface w/ FW System
Puncture Disk
Dev. Start System Assembly & EED Start Valve

## Slide 19: EDM-2 Start System
Major Accomplishments since Last PMR
Nearing Completion of EDM-2 Start System Components Drawings (Beginning Review)
Completed Development of Hermetic-Seal Laser-Weld Process for Gas Flask
Developed Gas Flask (Leak) Qualification Plan & Ordered Helium Leak Detector
  Near-Term Efforts
Complete EDM-2 Start System Components Drawings
Order EDM-2 Start System Parts
Task Description | Scheduled Completion Date | Status
Design EDM-2 Start System | 8/2/11 | 
Build EDM-2 Start Systems | 11/11/11 | 
Test EDM-2 Start System | 1/25/12 | 

## Slide 20: EDM-2 PPC & Wiring Harness Architecture
Four Flex Circuits Constitute Main Wiring Harness
Flex Cables Terminate in Blind-Mate Connector Rings
Flex Circuits Modeled w/ Sheet-Metal Tool
Flex Circuits Install into Condenser Before Boiler & Powertrain Module
Flex Circuits Routed Around Boiler

## Slide 21
EDM-2 PPC & Wiring Harness
Fwd Controller Board & Ring
Runs Powerplant Control Algorithm
20 Analog Instrumentation Channels
Interfaces to C&C Shell Section
Fwd Connector Board & Ring
Aft Connector Board & Ring
Aft Controller Board & Ring
Connected by PPS CAN to Fwd PPC Board
21 Analog Instrumentation Channels
Interfaces to Tail Section

## Slide 22
UNCLASSIFIED
EDM-2 PPS Operational States Draft v. 9/14/2011

## Slide 23: EDM-2 Powerplant Controls
Major Accomplishments since Last PMR
EDM-2 PPC Algorithms Baselined in Modified EDM-1 Code
Successfully Tested EDM-2 Algorithms in PPS Test PP2-1-1
Completed Design & Fab of Dev. EDM-2 Fwd Controller Board
Completed Powerplant Flex-Circuit Wiring Harness Mechanical Layout (4 Separate Harnesses) – PWB Layout Initiated
  Near-Term Efforts
Complete EDM-2 PPC Algorithm Coding into Simulink
Complete Design of EDM-2 Controller & Connector Boards
Complete PWB Layout of Powerplant Flex-Circuit Wiring Harnesses
Complete Design of PPC Automated Acceptance Test Set
Task Description | Scheduled Completion Date | Status
Design EDM-2 Controls | 8/19/11 | 
Build EDM-2 Controls | 12/30/11 | 
Test EDM-2 Controls | 4/18/12 | 

## Slide 24
EDM-2 Powerplant Schedule Drivers
Develop Turbine/Geartrain
Develop Feedwater System
Develop Boiler
Develop Condenser
PP2-1-1
CT2-1-1
TIME
Oct 2011
Develop Start System
Develop Oxidant System
PP2-2 Test Series
Fab EDM-2 Units
Fab EDM-2 Units
Fab EDM-2 Units
Fab EDM-2 Units
Fab EDM-2 Units
Fab EDM-2 Units
PP2-3 Test Series
Fab EDM-2 Units
Develop Control, Software, & Instrumentation

## Slide 25: ATT Powerplant Test – PP2-1-1
Test Date: 1 Aug 2011
Test Overview
Objectives
PRIMARY:
Evaluate dev. EDM-2 Powertrain Module Controllability & Transient Behavior w/ Breadboarded Start, Feedwater & Oxidant Subsystems using an EDM-1 PPC w/ dev. EDM-2 Control Algorithms.
Demonstrate powertrain module integration and performance of a dev. EDM-2 boiler coupled to a dev. EDM-2 turbine/geartrain.
SECONDARY:
Validate EDM-2 dynamometer transient behavior during speed changes.
Conclusions
Demonstated a rapid, robust powerplant start.
Demonstrated very good speed control through all speed transients.
Demonstrated good temperature control through all transients.
Demonstrated integration and operation of boiler to T/G with EDM-2 boiler mounts.
All objectives met.
Started and operated power module as planned for 226 seconds.
Engine operated at full range of speeds including speed up and down steps in increments from 500 to 3500 RPM.
Demonstrated 88.7 % fuel utilization.
Summary of Results
First Test in the EDM-2 Powerplant System Test series:
A dev. EDM-2 Boiler w/ Variable-Bore Tubing & a dev. EDM-2 Turbine/Gearbox were Close-Coupled in Vehicle Configuration .
Controlled by an EDM-1 PPC w/ dev. EDM-2 Control Algorithms.
Shaft Loading Provided by New Eddy-Current Dynamometer w/ Dynamic Load Control.

## Slide 26: ATT Powerplant System Test PP2-1-1
Test Article: Boiler-Turbine/Gearbox Assembly

## Slide 27: ATT Powerplant System Test PP2-1-1 Test Date: 1 Aug 2011
Test Article in Test Cell w/ Dynamometer

## Slide 28
ATT Powerplant System Test PP2-1-1 Test Date: 1 Aug 2011
Commanded & Measured Shaft Speed

## Slide 29
EDM-2 PPS Integration & Test
Major Accomplishments since Last PMR
Successfully Conducted Powerplant System Test PP2-1-1 (Power Module Controllability) on Schedule.
  Near-Term Efforts
Conduct Test Planning and Assembly of Hardware for Powerplant System Test PP2-2-1 (Condenser Module Performance Test).
Task Description | Scheduled Completion Date | Status
PP2-1-1 Power Module Controllability Test | 8/4/11 | Complete
PP2-2-1 Condenser Module Performance Test | 1/10/12 | 
PP2-2-2 Condenser Module Performance Test | 3/20/12 | 
PP2-3-1 Full Powerplant System Test | 6/19/12 | 
PP2-3-2 Full Powerplant System Test | 8/14/12 | 

## Slide 30: Summary
Design of the EDM-2 Powerplant Progressing Well
EDM-2 Parts Drawings Complete for T/G, Condenser, & FW System
Developmental EDM-2 Drawings Complete for all Other Subsystems – Deliverable Designs Nearing Completion
Powerplant Controls on Critical Path – No Schedule Impact Yet
Fabrication of EDM-2 Powerplant Parts Has Started
Ordered and Received Major Parts (Small Quantities) of the Turbine/Geartrain, Condenser, and Feedwater System
Developmental EDM-2 Hardware in-House for all other Subsystems
Powerplant System Testing Has Started
Successfully Completed First Powerplant System Test (PP2-1-1)
Working toward Second Powerplant System Test PP2-2-1, Scheduled for 1/10/12